## Sheet1
Teamify Sprint Performance
Sprint | 2020-07-09 | Date
Goal | "Get students on random teams after registration"
Forecast | 8 | Story Points
Days | Expected | Planned | Completed | Actual
2020-07-06 | 8 | 8 | 0 | 8
2020-07-07 | 5.3333 | 5 | 2 | 6
2020-07-08 | 2.6667 | 3 | 0 | 6
2020-07-09 | 0 | 0 | 0 | 6
Velocity | 8 | 8 | - | 2