## Sheet1
Rubric Tracking for Assignment 1: Team formation and product inception
| Task | Pts. | Status | Date | Result
| You have self-organized into a team. You have joined one of the "Scrum Teams" groups in Canvas. | 2.0 pts | Complete | 2020-06-27 | Used Stack to communicate and form a team. All members joined Team 2 in Canvas.
| You have named your team. You have created a Slack channel in the course Slack team with your team name. Course staff members can view the Slack channel. | 2.0 pts | Complete | 2020-06-27 | The team was named with a focus around the course project as "Teamify". A public channel was added to Slack following the team name.
| You have created a public git repository for your team and submitted the repo URL as the solution to this assignment. | 1.0 pts | Pending |  | The repository is created but has not yet been submitted as the solution. Each team member will perform an Assigment submission individually.
| The README in your git repo clearly lists your team name and roster. The roster includes each team member's name and the role they play on the team. | 1.0 pts | Complete | 2020-06-27 | Specification met as stated
| Your team has identified an open source product to create and given it a name. The name is clearly documented in your git repo's README. | 1.0 pts | Complete | 2020-06-27 | Teamify. Stated in README
| Your team has identified articulated a far vision for the product. It is clearly documented in your git repo's README. | 1.0 pts | Complete | 2020-06-27 | Specification met as stated
| Your team has identified articulated a near vision for the first iteration of the product, which you will build in this project. It is clearly documented in your git repo's README. | 1.0 pts | Complete | 2020-06-27 | Specification met as stated
| Your team has identified at least three stakeholder types whose needs are fulfilled by your product. They are clearly documented in your git repo's README. | 3.0 pts | Complete | 2020-06-27 | Specification met as stated
| At least one of your stakeholders is a real person whose needs are fulfilled by your product. The person's name is clearly documented in your git repo's README. | 1.0 pts | Complete | 2020-06-27 | Richard K. identified as "real person" stakeholder. Confirmed with Richard. Documented in README.
| Your team has constructed a detailed user persona for your real stakeholder. The user persona details are clearly documented in your git repo's README. | 1.0 pts | Complete | 2020-06-27 | User Persona for Richard documented in README
| Your team has constructed an initial product backlog. The backlog is stored in an online tool such as Trello or Google Spreadsheets. The URL of your backlog is clearly documented in your git repo's README. Course staff members can view your backlog. | 1.0 pts | Complete | 2020-06-27 | Specification met as stated
| There are at least 10 product backlog items in your product backlog. | 10.0 pts | Complete | 2020-06-27 | A total of 19 Product Backlog items were identified
| All product backlog items are expressed as excellent user stories. | 10.0 pts | Pending |  | User stories are provided for the top ten ranked items. Acceptance criteria are to be identified for the top item and documented as tasks on the board
| Your product backlog is ordered. Your rationale for how you ordered your backlog is clearly documented in your git repo's README. | 1.0 pts | Complete | 2020-06-27 | Specification met as stated
| You have a Definition of Ready for product backlog items. Your Definition of Ready includes at least these items: a) Title, b) User story opening sentence, c) Additional details, d) Estimated in story points. Your Definition of Ready is clearly documented in your git repo's README. | 5.0 pts | Deferred | 2020-06-28 | Deferred per Richard's instructions in Slack channel #summer2020. Points will be automatically awarded. Richard: "replied to a thread: So basically only product backlog ordering, nothing after? ... Yes, that's right. You do not have to create your definitions of Ready and Done, and you do not have to estimate your backlog items. Everyone will get credit for those rubric items."
| Estimate your PBIs, starting at the top of the backlog and working your way down to the bottom. Your backlog with estimated PBIs is stored in an online tool such as Trello or Google Spreadsheets. The URL of your backlog is clearly documented in your git repo's README. Course staff members can view your backlog. | 4.0 pts | Deferred | 2020-06-28 | Deferred per Richard's instructions in Slack channel #summer2020. See above
| You estimated your PBIs in story points. | 1.0 pts | Deferred | 2020-06-28 | Deferred per Richard's instructions in Slack channel #summer2020. See above
| You did a whole team relative size estimating activity. You documented the name of the activity in your README. | 1.0 pts | Deferred | 2020-06-28 | Deferred per Richard's instructions in Slack channel #summer2020. See above
| Only Development Team members participated in creating the estimates. You've made note of this in your README. | 1.0 pts | Deferred | 2020-06-28 | Deferred per Richard's instructions in Slack channel #summer2020. See above