## Sheet1
Rubric Tracking for Assignment 2: First Sprint
| Task | Pts. | Status | Date | Result
| You have a forecast of how many story points your team can complete during the sprint. The forecast is documented in your README. | 1.0 pts | Pending |  | We forecast 10pts. Based on the scale that was used in our estimation activity. Sprint Goal: Display resgistered students and team names. Need to update the README
| The rationale for your forecast is documented in your README. | 1.0 pts | Pending |  | We pulled items off the backlog to verify that the 10pt. forecast was a reasonable estimate, stopping at a PBI that has a higher point value than was thought to be achievable in this Sprint. Need to update the README
| You pulled stories into your sprint backlog. You pulled stories from the top of your product backlog. The aggregate size of the stories does not exceed your forecast. Only Development Team members participated in this activity. | 4.0 pts | Complete | 2020-07-02 | We held a Sprint Planning meeting and dragged the PBIs from the Product Backlog into the Sprint Backlog. The total story points for the Sprint Backlog match the initial forecast. All members of the team participated.
| All of the stories in your sprint backlog have size less than half your forecast velocity. If you noticed PBIs that are too large to get done in a sprint, you refined them by splitting them into smaller stories and estimating the smaller stories. | 1.0 pts | Complete | 2020-07-01 | Specification completed as written
| You decomposed stories into tasks. The tasks are clearly listed in your sprint backlog. | 2.0 pts | Complete | 2020-07-02 | Specification completed as written. Tasks are labeled and linked to PBI's in Trello.
| Your sprint backlog, including both stories and tasks, is represented in a kanban board. The kanban board, or a URL of the kanban board, is documented in your README. Richard can view the kanban board. | 3.0 pts | Pending |  | The Trello board includes both PBI's and tasks, which are linked. The progress of all work items is represented by the list (column) they are in. Need to update the README
| You have a sprint burndown chart. On the x-axis, you display time markers in units of 1 day. On the y-axis, you display story points remaining to get done. There is a linear curve descending from left to right; the leftmost point of the curve is number of story points in your sprint at sprint day 1; the rightmost point is 0 story points remaining on the last day of the sprint. The burndown chart, or the URL of the burndown chart, is document in your README. Richard can view the burndown chart. | 8.0 pts | Pending |  | An initial burndown chart is created.
| You have conducted multiple Daily Scrums. You have evidence of at least one daily scrum documented in your README. | 5.0 pts | Pending
| - What did you do in the last 24 hours that helped the Development Team meet the Sprint Goal? Annotate your team's response so it's clear which team members did which activities. | 5.0 pts | Pending
| - What will you do in the next 24 hours to help the Development Team meet the Sprint Goal? Annotate your team's response so it's clear which team members plan to do which activities. | 5.0 pts | Pending
| - Do you see any impediment that prevents me or the Development Team from meeting the Sprint Goal? What are the impediments? What is your impediment removal plan? | 3.0 pts | Pending
| Update your sprint backlog task board and burndown chart. Make sure the URLs or images are available in your GitHub repo's README. | 2.0 pts | Pending
| There is evidence that you paired or mobbed on your code. The evidence could be a photo or video of your team working together, or it could be some other kind of evidence. The evidence is included in your README. | 5.0 pts | Pending
| There is evidence that you are building your product test-first. (Fall semester only: There is at least 1 BDD / A-TDD test in your test suite, and it passes - 1 point.) There are at least 10 unit tests in your test suite, and they all pass. | 10.0 pts | Pending
| Your team conducts a Sprint Review. | 1.0 pts | Pending
| - Your product increment is working software. | 1.0 pts | Pending
| - At least one stakeholder attends your sprint review, and you provide evidence that your stakeholder was there. You revise your product backlog based on the feedback you receive. | 2.0 pts | Pending